## User stories
Sprint 1 planning
sprint goal | To test if the newly acquired hardware is compatible with the old software, and see if the team can reuse the old software
Story ID | URL | Title | State | Description | Author | Author Username | Assignee | Assignee Username | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate (hours) | Time Estimate | Time Spent
1 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/1 | As PO I want the new teams (us) to be properly informed of the available/existing hardware/software. | Open | (This is more a startup) Definition of done: - [ ] we as a team have knowledge of what projects and code is available - [ ] the team has a good understanding of the project as a whole. | Schilperoort,Lucas L.W. | I398389 |  | I338355 | No | No |  | 2021-02-25 13:29 | 2021-02-26 08:40 |  | Sprint 1 |  | This sprint, User story | 8 | 28800 | 0
2 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/2 | As PO I want a small test setup (at Strijp TQ) that allows us to test new software implementations for the hardware. | Open | Definition of done: - [ ] Hardware is available in TQ. - [ ] Hardware setup is installed at TQ (and easy to reproduce test setup) - [ ] tested with the software from Pozyx. | Schilperoort,Lucas L.W. | I398389 |  |  | No | No |  | 2021-02-25 13:30 | 2021-02-25 14:06 |  | Sprint 1 |  | This sprint,User story | 16 | 57600 | 0
3 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/3 | As PO I want research results proving whether the new sensors are compatible with existing software, and if not, what steps need to be taken to make them compatible. | Open | Definition of done: - [ ] Provide proof (research document / demo) if the sensors are compatible. - [ ] If changes must be made for compatibility, documentation must be included. | Schilperoort,Lucas L.W. | I398389 |  |  | No | No |  | 2021-02-25 13:31 | 2021-02-25 14:15 |  | Sprint 1 |  | This sprint,User story | 32 | 115200 | 0
4 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/4 | As PO I want a research document to see how scalable and expandable the current code is and propose a solution on how this will be done in the future. | Open | Definition of done: - [ ] Provide a research document which analyses the following aspects of the existing code - [ ] scalability - [ ] expandability - [ ] give advice for future implementation of these systems. | Schilperoort,Lucas L.W. | I398389 |  |  | No | No |  | 2021-02-25 13:31 | 2021-02-25 14:23 |  | Sprint 1 |  | This sprint,User story | 32 | 115200 | 0
5 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/5 | As PO I want a proposal for improvements of the software, making use of previous research. | Open | Definition of done: - [ ] document that provides an proposal for a new software solution or fixing/editing available software. | Schilperoort,Lucas L.W. | I398389 |  |  | No | No |  | 2021-02-25 13:31 | 2021-02-25 14:27 |  | Sprint 1 |  | This sprint,User story | 32 | 115200 | 0

## Burndown chart
week | Day | Remaining effort | effort spent | teammembers | 4
1 | 1 | 121.8 | 0 | hours per day | 7.25
1 | 2 | 121.8 | 0 | total amount of days | 6
2 | 3 | 121.8 | 0 | focus factor | 0.7
2 | 4 | 121.8 | 0
3 | 5 | 121.8 | 0
3 | 6 | 121.8 | 0