## User stories
Sprint 1 planning
sprint goal | To test if the newly acquired hardware is compatible with the old software, and see if the team can reuse the old software
Issue ID | URL | Title | State | Description | Author | Author Username | Assignee | Assignee Username | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate (hours) | Time Estimate | Time Spent
1 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/1 | As PO I want the new teams (us) to be properly informed of the available/existing hardware/software. | Closed | (This is more a startup) definition of done: - [x] we as a team have knowledge of what projects and code is available - [x] the team has a good understanding of the project as a whole. | Schilperoort,Lucas L.W. | I398389 | Vrösch,Ryan R. | I338355 | No | No |  | 2021-02-25 13:29 | 2021-03-18 12:15 | 2021-03-18 12:15:00 | Sprint 1 |  | User story | 8 | 28800 | 8
2 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/2 | As PO I want a small test setup (at Strijp TQ) that allows us to test new software implementations for the hardware. | Closed | definition of done: - [x] Hardware is available in TQ. - [x] Hardware setup is installed at TQ (and easy to reproduce test setup) - [x] tested with the software from Pozyx. | Schilperoort,Lucas L.W. | I398389 | Rutjens,Stijn S.C.H. | I409690 | No | No |  | 2021-02-25 13:30 | 2021-03-25 09:04 | 2021-03-25 09:03:52 | Sprint 2 |  | User story | 16 | 57600 | 16
3 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/3 | As PO I want research results proving whether the new sensors are compatible with existing software, and if not, what steps need to be taken to make them compatible. | Closed | definition of done: - [x] Provide proof (research document / demo) if the sensors are compatible. - [x] If changes must be made for compatibility, documentation must be included. | Schilperoort,Lucas L.W. | I398389 |  |  | No | No |  | 2021-02-25 13:31 | 2021-03-18 13:08 |  | Sprint 2 |  | This sprint,User story | 16 | 57600 | 8
4 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/4 | As PO, I want a research document to see how scalable and expandable the current code is and propose a solution on how this will be done in the future. | Closed | definition of done: - [x] Provide a research document which analyses the following aspects of the existing code - [x] scalability - [x] expandability - [x] give advice for future implementation of these systems. | Schilperoort,Lucas L.W. | I398389 | Schilperoort,Lucas L.W. | I398389 | No | No |  | 2021-02-25 13:31 | 2021-03-18 13:00 | 2021-03-18 08:24:45 | Sprint 1 |  | User story | 32 | 115200 | 32
5 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/5 | As PO I want a proposal for improvements of the software, making use of previous research. | Closed | definition of done: - [x] document that provides an proposal for a new software solution or fixing/editing available software. | Schilperoort,Lucas L.W. | I398389 | Meulensteen,Marc M.P.C. | I405582 | No | No |  | 2021-02-25 13:31 | 2021-03-18 13:05 | 2021-03-18 12:59:26 | Sprint 1 |  | User story | 32 | 115200 | 24
15 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/15 | As a developer I want the code to be redesigned and documented so it's easy to expand it in the future | Open | definition of done: - [ ] code is object oriented - [ ] design follows the SOLID principles | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:13 | 2021-03-25 08:43 |  | Sprint 2 |  | This sprint,User story | 80 | 288000 | 0
16 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/16 | As PO i want to add the possibility of showing more than 1 tag on the screen to make it possible to track multiple riders. | Open | definition of done: - [ ] More than 1 tag can be loaded at once - [ ] More than 1 tag can be shown at once - [ ] Multiple data sources are supported (MQTT, CSV, JSON) | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:14 | 2021-03-25 09:25 |  | Sprint 2 |  | This sprint,User story | 80 | 288000 | 0
17 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/17 | As PO i want a new and improved sensor system to read more accurate data | Open | definition of done: - [ ] The new hardware gets used by the system - [ ] The input data is filtered in real-time - [ ] The filter's output data is smooth | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:15 | 2021-03-25 09:21 |  | Sprint 2 |  | This sprint,User story | 16 | 57600 | 0

## Burndown chart
week | Remaining effort | effort spent
1 | 134.4 | 44.8 | 134.4
2 | 89.6 | 30.8 | 44.8
3 | 58.8 | 44.8
4 | 14 | 44.8
5 | 134.4 | 0
6 | 134.4 | 0
-14 uur in week 2 omdat ryan ziek was