## User stories
Sprint 3 planning
sprint goal | Get a basic implementation of our design
Issue ID | URL | Title | State | Description | Author | Author Username | Assignee | Assignee Username | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate (hours) | Time Estimate | Time Spent
15 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/15 | As a developer I want the code to be redesigned and documented so it's easy to expand it in the future (design document) | Open | 'definition of done: - [ ] design meets criteria set by the customer. - [ ] design follows the SOLID principles - [ ] design document provided following Fontys guidlines included feedback from peers Document: https://docs.google.com/document/d/1VvC0MIECwT8CxSWCf-9hQh8e4Y55AzAhO_G7WEFDPV4/edit# | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:13 | 2021-04-08 08:00 |  | Sprint 3 + project audit 1 |  | This sprint,User story | 80 | 288000 | 176400
16 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/16 | As PO i want to add the possibility of showing more than 1 tag on the screen to make it possible to track multiple riders. | Open | 'acceptance criteria: - [ ] More than 1 tag can be loaded at once - [ ] More than 1 tag can be shown at once - [ ] Multiple data sources are supported (MQTT, CSV, JSON) | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:14 | 2021-04-08 08:00 |  | Sprint 3 + project audit 1 |  | This sprint,User story | 80 | 288000 | 0
17 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/17 | As PO i want a new and improved sensor system to read more accurate data | Open | 'acceptance criteria: - [ ] The new hardware gets used by the system - [ ] The input data is filtered in real-time - [ ] The filter's output data is smooth | Vrösch,Ryan R. | I338355 |  |  | No | No |  | 2021-03-18 13:15 | 2021-04-08 07:42 |  | Sprint 2 |  | User story | 16 | 57600 | 0
20 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/20 | As a user of the new SMC program, I want to be able to save individual runs to my device | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-02 11:04 | 2021-04-08 07:56 |  |  |  | User story | 0 | 0 | 0
22 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/22 | As a user, I want to plot multiple runs on the same display from multiple data sources at the same time | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-02 11:09 | 2021-04-02 11:10 |  |  |  | User story | 0 | 0 | 0
23 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/23 | As a user I want to be able to select which measurement parameters get displayed on the screen (e.g. speed/height/g-forces) | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-02 11:10 | 2021-04-02 11:10 |  |  |  | User story | 0 | 0 | 0
24 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/24 | As a user I want to be able to see runs happen in real-time on the screen | Open | '- [ ] MQTT data is displayed as it is received - [ ] Data is shown per tag | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:34 | 2021-04-08 08:07 |  | Sprint 3 + project audit 1 |  | This sprint,User story | 0 | 0 | 0
25 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/25 | As a user I want to be able to save the measurement data | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:35 | 2021-04-08 07:36 |  |  |  | User story | 0 | 0 | 0
26 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/26 | As a user I want to be able to select a timestamp during playback | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:39 | 2021-04-08 07:39 |  |  |  | User story | 0 | 0 | 0
27 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/27 | As a user I want to be able to save and load program settings | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:40 | 2021-04-08 07:40 |  |  |  | User story | 0 | 0 | 0
28 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/28 | As a developer I want to be able to test my system manually without making use of unity | Open | 'Definition of done: - [ ] There is a .net frontend available - [ ] Code is compatible with unity - [ ] CI/CD implements unit tests | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:44 | 2021-04-08 08:06 |  | Sprint 3 + project audit 1 |  | This sprint,User story | 0 | 0 | 0
29 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/29 | As a user of the new SMC program, I want to be able to load individual runs from my device | Open |  | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:46 | 2021-04-08 07:56 |  |  |  | User story | 0 | 0 | 0
30 | https://git.fhict.nl/Lectoraat_HTES/uwb-positioning-area-51-2021vj/-/issues/30 | As a user I want to be able to connect to 1 MQTT server for recieving Pozyx data | Open | 'definition of done: - [ ] User is able to connect to 1 MQTT server User can set the following items: - [ ] Server address - [ ] Username - [ ] Password | Rutjens,Stijn S.C.H. | I409690 |  |  | No | No |  | 2021-04-08 07:52 | 2021-04-08 08:02 |  | Sprint 3 + project audit 1 |  | This sprint,User story | 0 | 0 | 0

## Burndown chart
week | Remaining effort | effort spent
1 | 134.4 | 44.8
2 | 89.6 | 30.8 | -14 uur omdat ryan ziek was
3 | 58.8 | 44.8
4 | 14 | 44.8
5 | 120.4 | 44.8
6 | 75.6 | 30.8 | -14 uur vanwege goeie vrijdag (ryan en stijn hebben doorgewerkt)
7 | 44.8 | 44.8 | -10 uur omdat Ryan de vrijdag heeft overgeslagen (en stijn de vrijdagmiddag)
7 | 0 | 44.8